ISO

International Organization for Standardization

Organisation Internationale de Normalisation

ISO/IEC JTC 1/SC 2

Coded Character Sets

ISO/IEC JTC 1/SC 2  N

18 August, 1996

Title:	Status report on NP 15285:  developing a TR on the topic, 
“An operational model for characters and glyphs”

Source:	Edwin Hart and Alan Griffee (acting editors)

Status:	Contribution by the acting editors

Action:	For the information of SC 2 and SC 18

Distribution:	ISO/IEC JTC 1/SC 2 and SC 18

This document describes (a) the activity for the last year since the SC 2 Plenary in Helsinki, (b) resolution of Japanese and Danish comments on the working draft distributed with the JTC 1, NP ballot, and (c) a plan for producing an approved Technical Report.  The current schedule calls for completing the Technical Report in the fall of 1998.

Activities

March, 1996

JTC 1 approved the NP (SC 2 N2677).  Japan voted against approval and had comments.  Denmark also had comments that were delivered late (WG 2 N1456).

June, 1996:

We submitted a preliminary working draft (WG 2 N1411) to SC 2/WG 2 for discussion at the WG 2 Meeting in Québec.  This was a revision of the working draft sent with the NP ballot (JTC 1 N3745).  The revision included editorial changes to clarify the text, and glyphs to illustrate the characters and the examples.  In WG 2 N1413, we also recommended a response to the Japanese comments on the NP ballot.

August, 1996:

At the WG 2 Meeting in Québec

In resolution, M31.1 (Character-Glyph Model), WG 2 voted to request that SC 2

- assign NP 15285 to WG 2

- appoint Edwin Hart and Alan Griffee as co-editors of the Technical Report.

- distribute the revised working draft of WG 2 N1411 to allow the National Bodies and Liaison Organizations adequate time to review and return comments for inclusion into a draft PDTR document to be considered at the January 1997, WG 2 Meeting in Singapore.  (The additional time would give the organizations more time to review the updated working draft so that comments could be incorporated into the draft PDTR.)

- approve a concurrent ballot for registration and PDTR distribution of the Technical Report when it is ready

Outside of the WG 2 meeting, an ad hoc committee met to discuss concerns and disposition of the Japanese and Danish comments, and to update the working draft (from the June 1996 draft) to resolve those concerns.  The committee members were:  Glenn Adams, Alan Griffee, Edwin Hart (chairman), Karl Larsson, Takayuki Sato, Keld Simonsen, and Johan van Wingen.

Disposition of comments on the NP ballot

Both Japan and Denmark had comments on the working draft distributed with the NP ballot (JTC 1 N3745).

The revised Scope in the August 1996 working draft of the TR appears likely to resolve the Japanese concerns.  Mr. Sato suggested a revision to the text contained in WG 2 N1413.  Later, the committee decided that the revised sentence about not fully developing the CJKV ideographic character issues should be moved from the Scope to the Introduction.  See WG 2 N1413R for the complete details of the response.

The committee was unable to fully satisfy the Danish concerns.  Denmark requested further development of the model to explain in more detail the concepts of character set, character repertoire, coded character set, code table, character encoding scheme, glyph and font.  Mr. Simonsen said that in particular, Denmark wanted further discussion of

- the various encoding schemes used in SC 2 (for example, ISO/IEC 646, the US 7-bit ASCII national version of ISO/IEC 646 (ANSI X3.4-1986), ISO/IEC 8859, ISO/IEC 10646.

- an explanation of the terms character set and character repertoire

The committee is working to address the Danish comments.

Plans

August, 1996:

At SC 2 Plenary Meeting

- Vote to assign the NP effort.

- Vote to appoint Edwin Hart and Alan Griffee as co-editors of the Technical Report.

- Vote to approve concurrent registration and distribution of the PDTR for approval.

September/October, 1996:

SC 2 distributes the August working draft for comments from SC 2 and SC 18.

November 30, 1996:

Requested deadline for comments.

December 15, 1996:

Submit a disposition of comments and a revised document as a draft PDTR for approval to process as a PDTR.

January, 1997:

Approve draft PDTR and submit to SC 2 for PDTR processing.

February, 1997:

SC 2 distributes a 3-month letter-ballot for TR registration and approval of the PDTR.

June, 1997:

Obtain results of the PDTR ballot and resolve comments.

Vote on resolution of the comments on the PDTR.

Vote to forward the revised draft of the Technical Report to SC 2 to approve it for balloting as a DTR.

SC 2 Plenary Meeting

Vote to forward the revised draft of the Technical Report to JTC 1 for processing as a DTR.

Fall, 1997:

JTC 1 issues the DTR ballot for a 4-month ballot.

Spring, 1998:

Receive results of the DTR ballot.

Submit disposition of comments for approval.

Summer, 1998:

Approve disposition of comments on the DTR and forwards to SC 2 Plenary for approval.

SC 2 Plenary approves resolution of comments.

Late Summer/Fall, 1998:

Submit final version of TR to ISO/IEC for publication.